## Sheet1
Risk No. | Risk item | Effect | Cause | Probability | Severity | Matrix Value | Actions to Minimize Risks | Final review
Project Planning
1.1.1 | Poor Judgement of team ability | Knockon affect on the product timeline. May affect the quality of particular areas of our project. Can also affect the relationship of not only the client and employer, but also between team members. | Tasks are distributed to individuals who have little confidence with said area. Assigned group varies in ability | 2 | 2 | 4 | Be honest with own personal ability. Be active in team discussions. Volunteer for tasks that you believe you are most suited for.
1.1.2 | Little contribution/poor performance from individuals | Can cause strain on other areas of the project, as well as on other team members who are forced to 'crunch' to finish parts others promised to complete. Can again affect deliverables and project timeline. | Issuing large or multiple tasks to one person without support from someone else. Team members agreeing to do more than expected. Bystander affect. | 1 | 3 | 3 | The scrum master should organise frequent meetings and discussion on progress, issues.
1.1.3 | Unrealistic deadlines | Can affect project timeline. Unneeded stress on team members who are given unrealistic deadlines to complete their tasks. Can cause tension between team members, which can in course lead to a lower quality product. | Little time to complete large tasks. Delays caused other issues stated in this document. | 1 | 2 | 2 | Set realistic deadlines for tasks. Structure tasks around accordingly. Individuals need to speak up if they believe targets are unrealistic
1.1.4 | Poor Leadership from Scrum Master | If the scrum master makes a lot of poor decisions and fails to monitor the progress of his team and their tasks, this can leave the project in a dire, non moving state. Could cause confusion for other team members with regards to their own personal goals they want to achieve. | Scrum master is poorly monitored by other team members. Wrong person assigned to position. Little effort made by scrum master. Poor decision choices | 1 | 3 | 3 | Other team members should support and give feedback when needed. Appoint suitable scrum master after lenghty discussion
1.1.5 | Poor Communication from team | Multiple team members working on the same task, when they could be either working together or on separate tasks. Could affect the quality of related or dependant tasks. Could cause confusion for other team members with current state of overall project. | Poor communication channels. Bystander effect. Little encourage from Scrum master. | 1 | 4 | 4 | require daily standups on team progression. Encourage constant communication throughout the day. Opt to have 2 member on each major task or not only shadow each other, but to also entice communication.
1.1.6 | Unfamiliarity with project resources | Inexperience with new resources can affect how quickly and efficiently we can complete tasks, espcially during the early stages of the project. May require extra time for familiarisation, which can again affect project timeline. | Using unfamilar technologies. Referenecing someone elses work for our project. | 4 | 3 | 12 | Take time to research and understand resources that we are working with. Read project brief throughly. Converse with client frequently for extra information.
Project Development
1.2.1 | No/Poor access to tools and technologies | Without the appropriate access and rights to certain parts of our platform, it means work just cannot be completed. This is massively affected when you consider we need account to access AWS and complete the task given. | AWS IAM Account not created for others. Trello board not shared. Any cloud based repositories not shared i.e. github, gdrive. Suitable permission for edditing for all. | 1 | 5 | 5 | At start of the project, set up access for each team member to all required software and platforms. Ensure to support those struggling with solutions and alternatives.
1.2.2 | Malicious access to project resources | If someone outside of our group was to access our project resources, not only would this show a major flaw in our security measures, but also allow people to manipulate our source material in malicious ways. | Malicious attack, poor IAM rules, public access to repositories, displaying sensitive information publically. | 2 | 5 | 10 | Create and follow strict security protocols. Use strong passwords and reset account details if breach is suspected.
1.2.3 | Issue with currrent build of technologies | If certain builds of tools and packages are not compable, this may cause our group to find alternatives to that tool. Some of the solutions may be tools we havent used, and could affect the quality of certain tasks and areas | Unfamiliar with technologies used. Poor support from developers. Software has been updated since original build. | 2 | 2 | 4 | Follow developers guide to technology. Familiarise team with any tools they are uncertain using. Revert to old version if more support is available.
1.2.4 | Poor Intenet connection | Can cause communcation issues within the team and cam cause inability to access particular tools and platforms such as Amazon Web Services. | Poor Internet Connection. Increased demanded on home network. Little alternative options. High traffic on internet provider. | 5 | 2 | 10 | Have alternatives to existing internet connection such as mobile hotstops and access to public internet. Little can be done to fix household internet due to modern position, contract ect.
1.2.5 | SQL Injection attacks | Common hacking technique that can drastically change or destroy my database, resulting in inefficiency of project deliverables. Illegal access to database and its data. | Poor security for project. "neglegtion of code for database and input of malicious table entries and code. concerns" | 1 | 3 | 3 | Have secure access protection for the website whilst in early development. Implement strong validation rules for tables to prevent malicious attacks
Health and Conditioning
1.3.1 | Eye Strain | Eye strain can have potential effects on the quality of work produced, and could effect the chance of meeting deadlines for deliverables | Heavy screen time, not taking frequent breaks from computer | 1 | 2 | 2 | Use 20/20/20 method
1.3.2 | Posture/Ergonomics related issues | Issues regarding posture and lack of ergonic support can not only affect the long term health of a developer, it can also affect the standard of work produced due to the undesireale conditions of the developer. Both probability and severity have increased from the last project, due to new working conditions and no access to benefactory equipment. | Lack of ergonical equipment, poor working conditions | 2 | 3 | 6 | Early signs of uncomfort cannot be seen and has had no impact on the project. Regular breaks where taken.
1.3.3 | Distruption due to current world events | Since our previous project, remote working has been piut in place to counter the ongoing COVID-19 Pandemic. Likely risks include illness, isolation, little access to work content and even possible closure of project. | Spread of COVID-19 | 5 | 5 | 25 | All of the distributions caused had happened prior and there where enough measures made prior to prevent any major impact to the project
1.3.4 | Illness | Falling ill during both the planning and development phases of the projec can result in a loss of time, as well as a drop in quality for the project. | Poor Hygiene, poor diet, stress | 2 | 3 | 6 | Light illness as an issue very early in the project but did not prevent me from completing work or attending calls
1.3.5 | Accomodation Issues | If this happens, one of more of our team members will lose over a days worth a worktime on their tasks. They would need time to readjust to their new environment. This can cause issue with current tasks, as well as tasks that are dependant on it. | One of our team members loses tenancy of their current accomodation | 3 | 3 | 9 | Support those moving as much as we can. Appoint multiple people to larger tasks. Adjust timeframe around peoples personal challenges
*: severity and probabiity of most the items lists may be affected by the COVID-19 Outbreak (16/03/20)
Key: Likelihood and Impact Scale uses a 1-5 scale, with 1 being not very strong and 5 being very strong